2012 Work Plan

Updated: January 2012

| Executive Committee Doreen Oneschuk (Education Committee) Bobbi Greenberg (Communications & Public Awareness Committee) Melody Isinger (Advocacy Committee) Bonnie Schroeder (Family & Caregiver Support Committee) Patricia Strachan (Research Utilization) Sharon Baxter (Secretariat) | Advocacy Committee (AC) Melody Isinger (Chair) Stephen Alexander Nadine Henningsen Denise Page Colleen Cash Bobbi Greenberg Sharon Baxter (Secretariat) |
| --- | --- |
| Education Committee (EC) Doreen Oneschuk (Chair) Rimmy Kaur Romayne Gallagher Marilyn Sapsford Mary Sculz Srini Chary Sharon Baxter (Secretariat) | Communications Committee (CC) Bobbi Greenberg (Chair) Shelagh Campbell Parlmer Judy Donovan Whitty Alison Pozzobon Marie-Josée Blier Sharon Baxter (Secretariat) |
| Family Caregiver Support Committee (FCSC) Bonnie Schroeder (Chair) Doug Kellough Tanny Nadon Marlene Chatterson Shelly Cory Sharon Baxter (Secretariat) | Research Utilization Committee (RUC) Pat Strachan (Chair) Mireille Lecours Vicki Lejambe Nuala Kenny Anna Pork Lala Christopher Klinger Le-Ann Dolan Sharon Baxter (Secretariat) |

2012 Committee Members

Advocacy Committee

| # | Work Plan Items | Action Items | Responsibility | Communication Strategy | Expected Outcome | Deliverables | Timeline | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Influence Government | Use key messages, asks and vignettes (leave behind pkgs). Include the synthesized Recommendations document, Gold Standards Remind member organizations developing briefs to Parliamentary Committees and MPs to identity palliative care issues. Advocate that the palliative and compassionate care committee become a permanent subcommittee of the health committee. Do a “day on the hill” or similar event. Present the framework and best practice to the Council of the Federation. | Committee Committee Committee & Secretariat Committee | Circulate updated leave behind packages to all QELCCC committees. Develop a letter stating Feds have a role to play in setting and coordinating national standards. | Use of QELCCC messaging | Use of tools and consistent messaging | Ongoing |  |
| 2 | Election toolkit | Adapt and update existing tools and circulate to members to encourage them to include in their election packets. Discuss with the AFN a letter of support re advocacy issues. | Committee Committee | Circulate to all QELCCC committees. | Identify end-of-life care as a socio-economic issue | Use of tools and consistent messaging | Spring 2012 |  |
| 3 | Monitor Parliament for members comments about end-of-life care | Review Hansard and contact member who commented thanking them for championing advanced care planning and end-of-life care. | Chair & Secretariat | TBD in conjunction w/Communications Committee. | Raise awareness of the QELCCC to Members of Parliament | Use Blueprint progress report, the key messages and asks. | Ongoing |  |
| 4 | Identify potential stakeholders to assist with integration of HPC | Advocate for better Accreditation Standards Facilitate uptake of new Model from the updated Norms of practice. Engage in discussion of national indicators and surveillance. | Advocacy, Research & Communications Committees | TBD in conjunction w/Communications Committee. | Build awareness for the need to integrate end-of-life care | Use Blueprint progress report, the key messages and asks. | Ongoing |  |
| 5 | Monitor news feeds for celebrities or notable person who mention HPC or ACP | Review news feeds and contact person who commented thanking them for championing advanced care planning and end-of-life care. | Committee & Secretariat | TBD in conjunction w/Communications Committee. | Raise awareness of the QELCCC to the general public | Use Blueprint progress report, the key messages and asks. | Spring 2012 |  |
| 6 | Liaise with provincial QELCCs or other relevant organizations. | Facilitate and assist Provincial associations adopt and/or adapt advocacy strategies and tools which assist with their specific advocacy priorities. In provinces that do not currently have a QELCCC, liaise with provincial HCP Chapters. Encourage development of provincial QELCCs and assist if asked with development. | Committee & Secretariat Committee | TBD | Encourage provincial QELCC’s | Use Blueprint progress report, the key messages and asks. | Summer-Fall 2012 |  |

Education Committee

| # | Work Plan Items | Action Items | Responsibility | Communication Strategy | Expected Outcome | Deliverables | Timeline | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Educational Inventory of Educational Tools: - Requires input from a number of Members - Asked to provide their input at current annual meeting | Review and refresh annually In several years, will follow up on its use: Wish List Requested all organizations update their resources and new organizations complete the inventory | Committee Chair & Secretariat Organizations, committee chair, secretariat Secretariat | E-blast | Updated Inventory Updated Inventory | Updated Inventory Updated Inventory | Annually-will attempt to have updated prior to Annual Meeting-by Dec. 2011 -now by Dec. 2012 |  |
| 2 | Position Statement/Discussion Document: Integration of Palliative Care into Chronic Diseases i.e. focus on cardiac, pulmonary, renal, dementia, neurodegenerative-likely multiple papers Editorial review of Integrating Palliative Care into Chronic Disease Management completed during face-to-face meeting Jan. 2012-Search terms included | Topics: -Capturing opportunities for integration of palliative care into chronic diseases-need for discussions between FP/Palliative Physicians/specialists, and inter-professional members-how to start discussions, opportunities for engagement, importance of ACP, resources, benefit of inter-professional team, systems approach, primary, secondary, tertiary care, cultural nuances—focus on Patient Centered Care (PCC) -Definitions: Nature of Palliative Care versus Palliative Approach versus Compassionate care versus Supportive Care Family Caregiving-care giver fatigue, stress, increasing responsibility --Subtopics of cardiac, renal, pulmonary disease, neurodegenerative-prognostic factors, symptom management (pain, dyspnea, fatigue)-need for educational translation/relationship building between specialists and specialist inter-professional teams | Education Committee- Health Care Canada Grant-Dr. Gallagher to work on Integration Section; Dr. Oneschuk to complete Letter of Intent for Concept Paper:Input from other QELCCC committees (subtopics) Research Committee re KT Project manager to assist with writing the Integration paper with input and editing provided the Education Committee | Target Audience: physicians (family physicians, specialists, inter-professional team members), QELCCC members, QELCCC members to pilot | Discussion Paper-a priority-topics considered for future projects/papers: standardization of university- based education (inter-professional and otherwise);collation of educational resources including assessment tools i.e EPEC-O, LEAP, established pathways; **palliative education in LTC settings (multiple comorbidities) and Homecare-possible lit search;assist QELCCC and community organizations in discussions on end-of-life e.g. ovarian, heart and stroke, etc. | Position Statement on Integration of palliative care into chronic disease management | Spring, early Summer 2012 |  |

Communication and Awareness Committee

| # | Work Plan Items | Action Items | Responsibility | Communication Strategy | Expected Outcome | Deliverables | Timeline | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Support QELCCC initiatives with timely dissemination of communications | Ensure members’ communications lead contacts are current. Collaboration with Coalition Committees to align effective, consistent messaging. Continue to ensure members have most current QELCCC collateral/news updates: - QELCCC E-Blasts Table of Contents - Weblinks to above - Executive Summary - Matte Article - Poster/abstract - Protocol for members sign-on for Coalition public documents/releases - 2010 Blueprint for Action - reminder of PowerPoint presentation re; Blueprint Work with Executive Committee to address raising public awareness/understanding of Coalition issues | Secretariat All committees Secretariat/ Committee Communication Committee | E-mail Through executive E-blast Next Issue – Post-Meeting Highlights -ACP Awareness Day, April 12 -Resource Summary & ask re updates | Efficient, effective, timely outreach. Consistent messages & understanding Consistent messages/ Understanding Efficient, effective, timely outreach. Advocacy | Up-to-date QELCCC communication contact list Consistent messaging Updated information for members Consistent messaging | Spring and Fall Ongoing Ongoing/ as material is updated Quarterly/ as needed Ongoing |  |
| 2 | Build Awareness of the QELCCC and Coalition Initiatives | Encourage members to incorporate a “declaration” of respective organization as QELCCC member and profile Blueprint for Action and 4 “asks” on website Support members to: - actively identify and foster Champions for end-of-life care (National, Provincial, Regional) -collect vignettes Build profile of QELCCC through media: - Write articles for publications - Explore other opportunities with relevant publications, i.e., Messages: (Dispelling the Myths, Taking Away the Fear, Role of PCMD, QELCCC Mandate, What is ACP?, Interview with Individual w Terminal Illness) QELCCC Award(s) for HPC Champion: -Strike all-committee task force to explore framework for possible award program John MacDermott Don Newman Penouff (hockey player) | Secretariat / Committee to provide example Committee Committee Exec. Committee/All | E-blast E-Blast E-Blast Zoomers, Cdn. Healthcare Network, Family Caregiver, CMA Publication E-blast | Awareness Awareness Awareness Awareness | Awareness Awareness Article Action Plan | Ongoing Ongoing Ongoing Spring 2013 |  |
| 3 | Advance Care Planning in Canada | Advance Care Planning project – Share strategic updates on ACP project milestones. Continue to ask Coalition members if they wish to join ACP distribution list. Following ACP Awareness Day, conduct survey with members re response/uptake of campaign (how did they use it?) | Secretariat Secretariat Committee | E-mail E-Blast E-Blast | Efficient, effective, timely outreach Efficient, effective, timely outreach | Awareness Complete distr list | Ongoing Ongoing Summer |  |
| 4 | Status of Parliamentary Committee on Palliative and Compassionate Care | Explore Parliamentary Committee on Palliative and Compassionate Care and informed keep QELCCC members. - letters to 51 committee members asking them to be champions and speak to 10 people “ the Power of 10” | Secretariat, Advocacy and Communications | E-mail | Consistent messages & understanding |  | Ongoing |  |
| 5 | Communications Strategy | Secure grant for communications strategy for QELCCC to leverage web technology for raising public awareness of end-of-life care. (Hike for Hospice, Blueprint for Action 2010, social marketing. webinars) Develop strategy for QELCCC and Integration Project Canadian Healthcare Network (e-newsletter) – explore re; publishing communications | Integration Project Committee and Secretariat | E-blast, Committees | Consistent Messages and understanding | Consistent messaging | 2012 | Not started Not started |

Family Caregiver Support Committee

| # | Work Plan Items | Action Items | Responsibility | Communication Strategy | Expected Outcome | Deliverables | Timeline | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Promote and recognize the role of family caregiving to Canadian society. | Confirm the ‘Invisible Work Day’ – First Tuesday of April Create a social marketing campaign for 2012. Create a #caregiversupport and have a tweetchat on day Share info with partners to post to their website Include as information in kit. Identify key messages about caregiving in Canada | Committee Committee and secretariat Advocacy Committee Committee | TBA with Communications Committee | Designated caregiver day and increased awareness of caregivers Consistent messages & understanding | Raise awareness for April 5 | Spring 2012 |  |
| 2 | Advocate for a caregiver strategy that provides supports for caregivers – financial and non-financial. | Liaise with other organizations and coalition (such as Canadian Caregiver Coalition, partner organizations) Liaise with finance department to promote and new tax credit Fact sheet on CCB – to help advocacy at both national and provincial In 2013 host a national day on the hill Work with partners and the Canadian Partnership Against Cancer to ensure grief and bereavement is part of the palliative care services | Committee and secretariat | E-blast, liaise with the Advocacy Committee | Increased capacity of the members to present the economic analysis of our issues. | Consistent messaging and increased awareness | Spring-Summer 2012 |  |
| 3 | Promote and increase awareness of information services and resources for caregivers | Create a dedicated space of the QELCCC e-blast for caregiving resources. Work with Virtual Hospice to add to the repository of resources on promising and emerging practices from the caregiving support community – CVH Exchange Fact finding exercise to catalogue supports and services for caregivers during transition points and moving across the continuum and life stages (children, moving to adult services, newly diagnosed, aging) | Committee and secretariat Committee and secretariat Committee and secretariat | E-blast CVH and QELCCC websites | Increased awareness of available caregiver resources | Featured caregiver section in e-blast | Fall 2012 |  |

Research Utilization Committee 2012

| # | Work Plan Items | Action Items | Responsibility | Communication Strategy | Expected Outcome | Deliverables | Timeline | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Blueprint recommendation implementation and next steps | Advocate for continued research funding in hospice palliative care to advance the Blueprint priorities. | Advocacy & Communications Committee Secretariat QELCCC members | QELCCC network and listserv | Continue to align the QELCCC research work with the new 10 year Blueprint for Action Strategy | Funding is available to advance the Blueprint priorities | Ongoing and Quarterly Review |  |
| 2 | Continue to foster linkages with CIHR funded Grants and other research projects focused on hospice palliative and end-of-life care. | Identify research findings that support the QELCCC mandate and advocate for access, support, quality, consistency and advanced care planning (blueprint priorities). Continue to update and share information from the Research Utilization Committee and the research list serve (recently developed at CHPCA). Advocate for the synthesis of the findings of the 2009 list of Net grants. Foster relationships with granting agencies (i.e,, CIHR) and knowledge translation partners to develop and maintain HPC as a priority | Secretariat Research Committee [Sharon Baxter & Patricia Strachan] Secretariat | Share information between Research Utilization/full QELCCC and hospice palliative care research community. | Increased knowledge of research outcomes in hospice palliative care. HPC / EOL as a priority in funding announcements & funded research | Communication with QELCCC, and the hospice palliative care community. Distribute 2009 Net grant list (Nuala?) Maintain current research funding | Ongoing and Quarterly Review |  |
| 3 | QELCCC role in knowledge translation of research findings relevant to hospice, palliative and end of life care | Encourage QELCC members to submit new and upcoming research initiatives and research findings relevant to the blueprint priorities to the Secretariat (submitted criteria must be summarized 3-5 bullet points, include blueprint priority label, and reference/link—no documents). | Secretariat QELCC Members | Share information with QELCCC members on an on-going basis. | Increased and improved knowledge dissemination amongst QELCC membership. | Secretariat to include a research section to the QELCC E-blast (sent out ~2 months) | Ongoing and Quarterly Review |  |
| 4 | Promote QELCCC members’ uptake of poster and workshop tools and other resources at their conferences and via other dissemination channels (i.e. social networking strategies). | Review and revise posters: Blueprint for Action; Progress Report 2008; Coalition Poster. Modify and include current ACP Poster. Remove gold standard poster. Add new poster on new project when approved. Encourage coalition members to use existing and new posters, workshops and presentations at their own conferences and meetings; members to report usage back to the Secretariat. | Secretariat, Research Utilization Committee QELCCC Members | Informing QELCCC members aware that these resources are available (E-blasts, website, listserv) | Uptake of poster and workshop tools and other resources at conferences | Strong research information sharing. Record of poster and workshop tool usage. | Ongoing and Quarterly Review |  |
| 4 | Explore the current status of general indicators for hospice, palliative and end of life care. | Advocate for the development of general and nationally adopted indicators for hospice, palliative and end of life care. | Secretariat Research Utilization Committee Education Committee |  | Development of general and nationally adopted indicators for hospice, palliative and end of life care. | Improved knowledge of indicators | Ongoing and Quarterly Review |  |